REAL-TIME fMRI DEMO ¦ PLANNING GUIDE Setting Up a Demo for a Class or Tour Everything to arrange, in order, so a live real-time fMRI demonstration runs smoothly.

This guide walks through everything needed to host a class or a tour and show the real-time fMRI demo on the scanner with a volunteer. Section 1 is the five-step overview, Section 2 has the action items and things to consider for each step, Section 3 is a sample tour schedule, and Sections 4-8 give a timeline, technical preparation, a day-of checklist, open questions to confirm, and contacts. Tick the boxes as you go.

| Tour coordinator | Teryn Wilkes - teryn.wilkes@colorado.edu |
| --- | --- |
| Tour length | 1 hour or 1.5 hours - chosen when you schedule |
| Hard deadline | The volunteer must contact Teryn at least 5 days before the tour (MR safety screening) |
| You bring | A set of demo tasks, a volunteer for the scanner, and the analysis and stimulus computers (Section 5) |
| Parking | One-time parking through ICS staff, if anyone needs it |

YOUR TOUR (FILL IN AS THINGS ARE CONFIRMED)

| Tour date and start time |  |
| --- | --- |
| Length | ☐ 1 hour ☐ 1.5 hours |
| Group and expected size |  |
| Volunteer (and backup) |  |
| Volunteer deadline (tour date minus 5 days) |  |
| Tasks, in run order |  |
| Parking needed? | ☐ yes ☐ no |

# 1.  The five steps at a glance

| 1 | Schedule a date | Pick a date with Teryn Wilkes. Tours run 1 or 1.5 hours. |
| --- | --- | --- |
| 2 | Select the demo tasks | Choose example fMRI tasks that fit the tour length; Teryn confirms they fit. |
| 3 | Arrange parking (if needed) | Work with ICS staff to get one-time parking. |
| 4 | Arrange a volunteer | Someone to be the human in the scanner. They must contact Teryn at least 5 days before the tour for MR safety screening. |
| 5 | Show up! | Arrive early, set up, and run the demo. |

# 2.  Action items and things to consider

## Step 1 - Schedule a date with Teryn

ACTION ITEMS

☐	Email Teryn Wilkes (teryn.wilkes@colorado.edu) with a few proposed dates and whether you want a 1-hour or 1.5-hour tour.

☐	Tell Teryn who the group is (class, visitors, prospective students) and roughly how many people.

☐	Get a confirmed date and start time in writing, and add it to the "Your tour" box above.

☐	Work backwards from the date: every deadline in Section 4 keys off it.

THINGS TO CONSIDER

Tour length drives everything else. A 1-hour tour has room for fewer tasks than a 1.5-hour tour (Step 2).

Book early. The volunteer needs at least 5 days for screening, and parking and volunteer availability depend on the date.

Ask Teryn whether there is a maximum group size or a preferred time of day (see Section 7).

## Step 2 - Select the example fMRI demonstration tasks

ACTION ITEMS

☐	Choose the set of tasks from the table below and write them into the "Your tour" box in the order you want to run them.

☐	Send the list to Teryn. Teryn will help make sure the selected tasks can be completed in the time of the scheduled tour.

☐	Note the run order and the --run numbers you will use (Section 5).

☐	Decide who runs the analysis computer and who runs the stimulus computer on the day.

TASK OPTIONS

| Task (name shown to the participant) | Command name | Run length | With instructions | Notes |
| --- | --- | --- | --- | --- |
| Visual Perception Task (checkerboard vs rest) | checkerboard_1cond | 260 s (4:20) | ~6-7 min | Strong, fast visual cortex response. The most reliable demo. |
| Visual Perception Task (left vs right) | checkerboard_2cond | 204 s (3:24) | ~5-6 min | Each half of the visual field drives the opposite hemisphere. Shortest task. |
| Voluntary Movement Task | motor | 250 s (4:10) | ~6 min | Squeeze left or right hand. Opposite motor cortex lights up. Easy to explain. |
| Hand Guessing Game | motor_guessing | 250 s (4:10) | ~6 min | Volunteer secretly picks a hand; the group guesses from the live map. Interactive and fun. |
| Blackjack Game | gambling | 298 s (4:58) | ~7 min | Reward task (win vs lose). Effects are subtler, so it is a weaker choice for a short tour. |

Run lengths come from each task's design file. "With instructions" is a planning estimate: the run plus about 2 minutes for the on-screen instructions and resetting. A sixth task, checkerboard_3cond (300 s), also exists but is more complicated to explain and is not recommended for a tour.

THINGS TO CONSIDER

Total time. Add up the "with instructions" column and compare it with the tour length. The rest of the tour also needs time for the introduction, getting the volunteer safely into the scanner, any set-up scans, and questions. Ask Teryn how much time that takes (Section 7).

A quick, reliable start. The Visual Perception tasks give the clearest activation soonest, so they make a good first task. As a starting point, the sample schedule (Section 3) has a 25-minute demo block, which fits about three tasks; Teryn has the final say.

Hand Guessing Game. The volunteer must keep the chosen hand secret from the group, so brief them beforehand and have them choose only once they are in the scanner. It works best when the audience can see the live view.

Sample output. The demo bulletin (docs/realtime_demo_bulletin.pdf) shows what each task looks like and is a good handout.

## Step 3 - Parking (if needed)

ACTION ITEMS

☐	Decide whether anyone needs parking: the group, the volunteer, or you.

☐	If yes, contact ICS staff to get one-time parking for the tour date.

☐	Confirm with ICS staff what they need from you (for example the date, arrival time and number of vehicles) and how far ahead to ask.

☐	Send directions and parking details to everyone arriving by car.

THINGS TO CONSIDER

Request parking as soon as the date is confirmed, since lead time is not known.

The INC is in the Center for Innovation and Creativity (CINC), 1777 Exposition Drive. Directions: https://www.colorado.edu/mri/participants/directions-inc

## Step 4 - Arrange a volunteer to be the human in the scanner

Deadline: the volunteer must contact Teryn (teryn.wilkes@colorado.edu) at least 5 days before the scheduled tour so Teryn can make sure they are safe to enter the MR environment.

ACTION ITEMS

☐	Recruit a volunteer. Someone who has been scanned before, or who is comfortable in small spaces, is easiest.

☐	Send the volunteer the MR safety screening form (INC website): INC MRI safety screening form (PDF)

☐	Tell the volunteer to contact Teryn by email at least 5 days before the tour, and put that date in the "Your tour" box. Ask Teryn exactly how she wants the form returned.

☐	Tell the volunteer to arrive 10 minutes before the tour starts to change into scrubs.

☐	Confirm with Teryn that the volunteer has been cleared before the tour goes ahead.

☐	Brief the volunteer on the tasks you chose (what they will see and what to do). For the Visual Perception tasks, remind them to keep their eyes on the center of the screen.

THINGS TO CONSIDER

MR safety is not optional. Only someone cleared by Teryn can enter the scanner room. A standard screen covers things such as pregnancy, metal in the body and claustrophobia.

Line up a backup volunteer (also screened at least 5 days ahead) in case the first one cannot make it.

Ask Teryn what the volunteer should wear and leave at home, and whether any other paperwork applies (Section 7).

The volunteer needs to lie still for several minutes at a time. Tell them what to expect, including the noise and the small space.

## Step 5 - Show up!

Arrive early enough to set up and test before the group arrives. The day-of checklist is in Section 6, and the technical preparation that should happen before then is in Section 5.

# 3.  Sample tour schedule

A sample running order for a 1 hour 15 minute tour. Times are minutes after the tour starts (+0:00).

| Time | Activity | Notes |
| --- | --- | --- |
| -0:10 | Volunteer arrives and changes into scrubs | The volunteer should arrive 10 minutes early. |
| +0:00 | Welcome! Meet in the CINC lobby |  |
| +0:00 - 0:25 | Tour of the MRI facilities | Teryn Wilkes leads. |
| +0:25 - 0:35 | Demo volunteer safety screening | The advance contact with Teryn at least 5 days before (Step 4) still applies. |
| +0:35 - 1:00 | fMRI demo | About 25 minutes: roughly three tasks at ~6 minutes each (Step 2 table). Teryn confirms the fit. |
| +1:00 - 1:15 | Wrap up and questions |  |

This sample runs 1 hour 15 minutes, so it fits a 1.5-hour tour slot with time to spare. For a 1-hour slot, ask Teryn what to trim (for example, fewer tasks in the demo).

THINGS TO CONSIDER

Be ready before the group arrives. The demo starts at +0:35, so the analysis and stimulus computers should already be set up and tested (Section 5).

How many tasks fit depends on how much of the demo block goes to positioning the volunteer in the scanner. Ask Teryn (Section 7).

# 4.  Timeline

Only the 5-day volunteer deadline is fixed. The other lead times are suggestions; adjust them with Teryn.

| When | Action | Owner |  |
| --- | --- | --- | --- |
| As soon as possible | Contact Teryn; agree the date, start time and 1 or 1.5 hour length. | Organizer | ☐ |
| Once the date is set | Request one-time parking from ICS staff, if needed. | Organizer | ☐ |
| Once the date is set | Recruit a volunteer (and a backup) and send them the safety screening form. | Organizer | ☐ |
| About 2 weeks before | Send your task list to Teryn to confirm it fits the tour length. | Organizer, Teryn | ☐ |
| 5 days before (deadline) | Volunteer has contacted Teryn and is cleared for the MR environment. | Volunteer, Teryn | ☐ |
| 2-3 days before | Dry run: start each chosen task with the mock scanner and confirm the live view updates (Section 5). Brief the volunteer. | Organizer | ☐ |
| 1 day before | Confirm parking and arrival instructions with the group; remind the volunteer to arrive 10 minutes early; charge and pack equipment. | Organizer | ☐ |
| Day of | Show up early and work through Section 6. | Everyone | ☐ |

# 5.  Technical preparation

Do this before the tour, ideally as a full dry run 2-3 days ahead. The project's own guides (PREFLIGHT.md, TESTING.md, INSTALLATION.md) have the detail.

ANALYSIS COMPUTER (RUNS THE LIVE ANALYSIS AND VIEWER)

☐	Docker Desktop is running and the brainiak/rtcloud image is already downloaded (do not rely on venue Wi-Fi).

☐	Real-time DICOM export from the scanner is enabled and reaches this computer through dicom_bridge.py (PREFLIGHT.md items 1-2). Ask Teryn or the scanner operator how to enable it on the day.

☐	dicomDir is empty before each run, so old files cannot mix with the new scan (PREFLIGHT.md item 3).

☐	The live viewer opens in a browser: outDir/live/viewer.html. It shows a template of the task until the first volume arrives.

☐	Mirror or extend the display so the group can see the viewer on a large screen.

STIMULUS COMPUTER (SHOWS THE TASKS TO THE VOLUNTEER)

☐	MATLAB with Psychtoolbox is installed and stimuli_ptb/test_ptb_install.m runs. (PsychoPy with stimuli/test_psychopy_install.py is the alternative.)

☐	The display, response device and scanner trigger work. The tasks start on a scanner trigger key, or SPACE for a desk test.

☐	The task list and order in run_battery match your plan (see the bulletin, page 3).

RUN NUMBERS AND COMMANDS

Start each task's analysis with ./quickstart.sh <task> --run N. The --run flag is optional and sets the scan run number. Using the same order as the stimulus battery keeps them in step, for example:

| # | Analysis command | Stimulus function in run_battery |
| --- | --- | --- |
| 1 | ./quickstart.sh checkerboard_1cond --run 7 | checkerboard_1cond_task |
| 2 | ./quickstart.sh checkerboard_2cond --run 9 | checkerboard_2cond_task |
| 3 | ./quickstart.sh motor --run 11 | motor_task |

Add more tasks the same way (--run 13, --run 15, and so on), and only list the tasks you actually chose. Command names for every task are in the Step 2 table.

FALLBACK IF THE SCANNER DATA DOES NOT STREAM

utils/mock_scanner.py replays a recorded scan through the same pipeline (TESTING.md, section 4). It keeps the demo going, but tell the group it is a replay, not the volunteer's live scan.

Have a printed copy of the demo bulletin and a few screenshots ready as a last resort.

# 6.  Day-of checklist

BEFORE THE GROUP ARRIVES

☐	Arrive early. Confirm with Teryn when the space and scanner are available for set-up.

☐	Park (if you arranged parking) and bring what you need to be let into the building.

☐	Confirm with Teryn that the volunteer is cleared, and that the backup is on standby if needed.

☐	The volunteer arrives 10 minutes early and changes into scrubs.

☐	Set up the analysis and stimulus computers and the large display. Start Docker and run a short mock-scanner test.

☐	Open the live viewer and check it shows the task template.

☐	Line up the task order and run numbers (Section 5) on a printed card.

DURING THE TOUR

☐	Welcome the group and explain what real-time fMRI is (page 1 of the bulletin has a short version).

☐	The volunteer is set up in the scanner by Teryn or the scanner operator, following the site's MR safety procedures.

☐	Before each task: press SPACE at the "Up next" screen when the analysis is ready and the volunteer knows what to do.

☐	While each task runs, point out the activation map and the measured versus predicted curves as they appear.

☐	Keep an eye on the clock against the tour length. Drop the last task if you are running over.

AFTER THE TOUR

☐	Thank the volunteer and the group.

☐	Ask Teryn how demo data (DICOMs and outDir) should be handled, then clear them from dicomDir and outDir as advised.

☐	Shut down the containers and pack up. Note anything to improve for next time.

# 7.  Questions to confirm with Teryn

These are the details this guide does not know. Ask them when you schedule, and write the answers in.

☐	Is there a maximum group size, and how many people can be in the scanner control room?

☐	How much of the 1 or 1.5 hours is needed for the introduction, safety, positioning the volunteer and any set-up scans? (This sets how many tasks fit.)

☐	How is real-time DICOM export turned on for a tour, and who does it?

☐	How should the volunteer return the safety screening form, and is any other paperwork or consent needed?

☐	What should the volunteer wear, bring or leave behind?

☐	When can we get into the space to set up, and how early should we arrive?

☐	How should the demo scan data be stored or deleted afterwards?

☐	Are photos or video of the tour allowed?

☐	Can a backup volunteer be screened in the same way?

# 8.  Contacts and links

| Tour scheduling, task selection, volunteer screening | Teryn Wilkes - teryn.wilkes@colorado.edu |
| --- | --- |
| Parking | ICS staff (one-time parking) |
| MRI safety screening form | https://www.colorado.edu/mri/sites/default/files/2026-04/INC_MRI%20Intake%20Form_Jan2020.pdf |
| INC website | https://www.colorado.edu/mri |
| Directions and parking | https://www.colorado.edu/mri/participants/directions-inc |
| Demo project | https://github.com/intermountainneuroimaging/realtimeDemo |